## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Consolidated project backlog — reconstructed retrospectively from project work; exact sprint dates and formal sprint records were not maintained.
Sprint 1 | Sprint 1 (consolidated) | US-01 | As a student, I want to upload and parse my resume so that my career profile can be created from resume content. | Must | Resume parser and file upload flow | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-02 | As a student, I want to view and manage my candidate profile so that my education and skills are available for career workflows. | Must | US-01; profile/database modules | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-03 | As a student, I want to search internship/job listings so that I can find relevant opportunities. | Must | Job dataset in data/jobs.csv | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-04 | As a student, I want job recommendations based on my profile so that I can prioritize relevant roles. | Must | Candidate profile; job dataset; vector search/matching modules | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-05 | As a student, I want to identify skill gaps for a selected role so that I know which skills to improve. | Must | US-02; job requirements and matching workflow | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-06 | As a student, I want resume improvement assistance so that I can strengthen my application. | Should | Candidate profile/resume content | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-07 | As a student, I want to generate a job-specific cover letter so that I can tailor my application. | Should | Selected job details and candidate profile | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-08 | As a student, I want interview preparation for a selected role so that I can practise role-relevant questions. | Should | Selected job/role details | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-09 | As a student, I want career guidance through a career assistant so that I can get support with career-related questions. | Should | Career assistant module and available project context | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-10 | As a student, I want to track job applications and their status so that I can manage my application progress. | Must | SQLite application-tracking storage | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-11 | As a project evaluator, I want a single Streamlit interface for the features so that the application is easy to navigate. | Must | Feature modules integrated in app.py | Project Developer | Completed
Sprint 1 | Sprint 1 (consolidated) | US-12 | As a project evaluator, I want the project documented and deployed so that the application can be reviewed online. | Should | GitHub repository; Streamlit Community Cloud configuration | Project Developer | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task estimates are retrospective planning estimates (not original time-sheet data). Exact task start/completion dates and actual day-by-day hours were not recorded; NR means Not Recorded.
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
CONSOLIDATED PROJECT BACKLOG — RETROSPECTIVE RECONSTRUCTION (not a contemporaneous daily time log)
US-01 | T-01 | Set up Streamlit application entry point and page navigation | Not recorded | Not recorded | Project Developer | Development | Completed | 4 | bar: Day 1 to Day 14
US-01 | T-02 | Implement resume upload and text extraction using supported document parsing | Not recorded | Not recorded | Project Developer | Development | Completed | 6 | bar: Day 1 to Day 14
US-02 | T-03 | Implement candidate profile extraction and profile storage using SQLite | Not recorded | Not recorded | Project Developer | Development | Completed | 6 | bar: Day 1 to Day 14
US-03 | T-04 | Prepare and integrate internship/job listings in data/jobs.csv | Not recorded | Not recorded | Project Developer | Data preparation | Completed | 4 | bar: Day 1 to Day 14
US-04 | T-05 | Implement job knowledge-base/vector-store workflow using ChromaDB and Sentence Transformers | Not recorded | Not recorded | Project Developer | Development | Completed | 8 | bar: Day 1 to Day 14
US-04 | T-06 | Integrate job matching and display ranked job recommendations | Not recorded | Not recorded | Project Developer | Development | Completed | 6 | bar: Day 1 to Day 14
US-05 | T-07 | Implement skill-gap analysis for a selected job role | Not recorded | Not recorded | Project Developer | Development | Completed | 5 | bar: Day 1 to Day 14
US-06 | T-08 | Implement resume-assistance workflow | Not recorded | Not recorded | Project Developer | Development | Completed | 4 | bar: Day 1 to Day 14
US-07 | T-09 | Implement job-specific cover-letter generation | Not recorded | Not recorded | Project Developer | Development | Completed | 4 | bar: Day 1 to Day 14
US-08 | T-10 | Implement interview-preparation workflow for selected roles | Not recorded | Not recorded | Project Developer | Development | Completed | 4 | bar: Day 1 to Day 14
US-09 | T-11 | Integrate career assistant feature | Not recorded | Not recorded | Project Developer | Development | Completed | 4 | bar: Day 1 to Day 14
US-10 | T-12 | Implement application tracker and SQLite-backed application records | Not recorded | Not recorded | Project Developer | Development | Completed | 6 | bar: Day 1 to Day 14
US-11 | T-13 | Integrate feature modules into the main Streamlit application and refine navigation | Not recorded | Not recorded | Project Developer | Integration | Completed | 6 | bar: Day 1 to Day 14
US-11 | T-14 | Run manual checks of dashboard and feature navigation; address observed interface issues | Not recorded | Not recorded | Project Developer | Testing / fixes | Completed | 4 | bar: Day 1 to Day 14
US-12 | T-15 | Publish source code and documentation to GitHub while excluding private runtime files | Not recorded | Not recorded | Project Developer | Version control | Completed | 4 | bar: Day 1 to Day 14
US-12 | T-16 | Deploy Streamlit app and troubleshoot deployment/database configuration | Not recorded | Not recorded | Project Developer | Deployment / fixes | Completed | 6 | bar: Day 1 to Day 14
US-12 | T-17 | Prepare project README, installation/user guides, milestone reports, changelog, and contribution guidance | Not recorded | Not recorded | Project Developer | Documentation | Completed | 6 | bar: Day 1 to Day 14
US-12 | T-18 | Upload project screenshots and update repository details/live demo link | Not recorded | Not recorded | Project Developer | Documentation | Completed | 3 | bar: Day 1 to Day 14
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Consolidated | Checkpoint 1 | Formal dated stand-up minutes were not retained; this is a retrospective project checkpoint. | Confirmed core application scope: resume/profile, jobs, skill gaps, assistance, interview prep, career assistant, and tracker.
Consolidated | Checkpoint 2 | Resume parsing and profile persistence required integration across parser and database modules. | Integrated resume/profile workflow with local SQLite-backed storage.
Consolidated | Checkpoint 3 | Job listings and matching required a consistent dataset and retrieval workflow. | Used data/jobs.csv and integrated the job matching/vector-search workflow.
Consolidated | Checkpoint 4 | External OpenAI API quota became unavailable during development. | Switched extraction to a rule-based fallback rather than relying on a working API quota.
Consolidated | Checkpoint 5 | Streamlit Cloud initially reported a SQLite OperationalError during deployment. | Deployment troubleshooting was performed; the user later confirmed the live application was working. Exact fix date was not recorded.
Consolidated | Checkpoint 6 | A navigation/sidebar integration issue and an application-tracker display mismatch were observed during development. | Subsequent project updates were made; the user later reported live features working. Exact individual fix details were not retained.
Consolidated | Checkpoint 7 | Project documentation and repository screenshots needed organizing for review. | Updated repository documentation, added a live demo link, and uploaded 13 screenshots to the screenshots folder.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Consolidated project review | Not recorded | Not recorded | Project Developer | Keep modules organized and continue documenting working features as they are completed. | Avoid making undocumented assumptions about exact dates, effort logs, or defect-fix details. | Continue using incremental feature development, manual checks, GitHub documentation, and a public demo. | Create formal sprint dates, daily stand-up notes, actual effort logs, and test evidence for future iterations.
2 | N/A — no separate sprint retrospective record | Not recorded | Not recorded | Project Developer | N/A — not separately recorded | N/A — not separately recorded | N/A — not separately recorded | Only one consolidated retrospective was prepared; no additional sprint-specific records were supplied.
3 | N/A — no separate sprint retrospective record | Not recorded | Not recorded | Project Developer | N/A — not separately recorded | N/A — not separately recorded | N/A — not separately recorded | Only one consolidated retrospective was prepared; no additional sprint-specific records were supplied.
4 | N/A — no separate sprint retrospective record | Not recorded | Not recorded | Project Developer | N/A — not separately recorded | N/A — not separately recorded | N/A — not separately recorded | Only one consolidated retrospective was prepared; no additional sprint-specific records were supplied.
5 | N/A — no separate sprint retrospective record | Not recorded | Not recorded | Project Developer | N/A — not separately recorded | N/A — not separately recorded | N/A — not separately recorded | Only one consolidated retrospective was prepared; no additional sprint-specific records were supplied.
6 | N/A — no separate sprint retrospective record | Not recorded | Not recorded | Project Developer | N/A — not separately recorded | N/A — not separately recorded | N/A — not separately recorded | Only one consolidated retrospective was prepared; no additional sprint-specific records were supplied.
7 | N/A — no separate sprint retrospective record | Not recorded | Not recorded | Project Developer | N/A — not separately recorded | N/A — not separately recorded | N/A — not separately recorded | Only one consolidated retrospective was prepared; no additional sprint-specific records were supplied.