## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Project Developer | Not recorded | Streamlit Community Cloud deployment initially failed with sqlite3.OperationalError while opening the configured SQLite database path. | Not formally tracked | Project Developer | Logical | Deployment/database troubleshooting was performed. The user later confirmed the live app was working; the exact corrective change and date were not retained. | Not recorded | Closed | Historical deployment issue. Exact resolution details were not documented in the available project notes.
2 | Project Developer | Not recorded | Sidebar/navigation integration did not display as intended after a code merge. | Not formally tracked | Project Developer | User Interface | The main Streamlit app was subsequently replaced/updated to resolve the sidebar merge issue. | Not recorded | Closed | The issue was reported as resolved during project work.
3 | Project Developer | Not recorded | The dashboard displayed application-tracker data, but the My Applications view showed no applications for the same test state. | Not formally tracked | Project Developer | Logical | Tracker/database workflow was revisited in subsequent project updates. The user later reported that live features were working; exact fix details were not retained. | Not recorded | Closed | Historical mismatch; status marked closed based on the later user confirmation that the live app worked.
4 | Project Developer | Not recorded | OpenAI API quota was exhausted, preventing continued use of the API-based candidate extraction path. | Not formally tracked | Project Developer | Others | A free rule-based extraction fallback was used so development could continue without relying on the exhausted API quota. | Not recorded | Closed | Workaround implemented; this was an external API quota limitation rather than a confirmed application-code defect.
5 | Project Developer | Not recorded | An application-tracker options/files view displayed a 'no such files are found' message during development. | Not formally tracked | Project Developer | Logical | The tracker workflow was revisited during subsequent updates; the user later reported the live app features were working. Exact fix details were not retained. | Not recorded | Closed | Historical issue. No exact date or individual corrective commit was recorded.

## Sheet2
Logical | Defect classification values used in the tracker
User Interface | UI and layout defects
Maintainability | Code clarity and maintainability
Standards | Coding or documentation standards
Others | External dependency, environment, or other issue